## FY16 Projects
ID# | Project | Location | Priority | Schedule | Weeks | Primary Funds | Secondary Funds | Budget | YTD | Available | M&O Work | Contract Out | Total | Program Review Approved | Description | Notes
54 | Trailer Park | Aquatic Ctr | 5 | Denied moving forward | 26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Contract Work - pave and infrastructure for trailers, relocate trailers from campus
55 | AEC HVAC/Boiler project | AEC | 1 | Design in prog | 24 | 113 |  | 1500000 | 0 | 1500000 | 0 | 1500000 | 1500000 |  | Remove Units over Large Gym, install new units on North side. Approved in PR14
56 | Sand Volleyball / Tennis Courts | Aquatic Ctr | 3 | Design in prog |  | 113 |  | 2000000 | 0 | 2000000 | 0 | 2000000 | 2000000 | FY15 | Install three courts in old aquatic center. Approved in PR15. | 10K for Design Completed
57 | South Campus Wy Parking/Roundabout | Campus | 3 | Design in prog | 12 |  |  | 250000 | 0 | 250000 | 0 | 250000 | 250000 |  | Create new parking on S Campus Way, roundabout, and sidewalks
58 | Pirate's Walk/ ASVC Pirate's Plaza | Campus | 2 | Design in prog | 52 | 713 | 412 | 1700000 | 0 | 1700000 | 0 | 1700000 | 1700000 |  | New walkways, lighting, landscaping, and plaza area
59 | Remodel Shops Building | M&O | 1 | Design in prog |  | 412 |  | 325000 | 0 | 325000 | 0 | 325000 | 325000 | 2015 | Replace siding, roofing, doors, and framing on Shops building | org 39958
60 | HVAC - Math Science | MS | 1 | Design in prog | 12 | 419 |  | 1500000 | 189194 | 1310806 | 0 | 1500000 | 1500000 | 2012 | Provide additional ventilation, heating and cooling for southern half of MS
61 | Math Science Boiler project | MS | 2 | Design in prog | 8 | 412 |  | 130000 | 0 | 130000 | 0 | 130000 | 130000 |  | Replace 5 boilers with 3 new boilers
62 | Traffic mitigation at Wright Library | WEC | 2 | Design in prog |  | 415 | 417 | 230000 | 0 | 230000 | 0 | 230000 | 230000 |  | Widened right lane to East Campus Way, restripe Wright Library Parking lot, install new driveway to Day Rd
63 | WEC Install Water & Gas Lines | WEC | 3 | Design in prog | 2 | 419 |  | 8000 | 0 | 8000 | 4000 | 4000 | 8000 |  | New gas and water to connect to Campus gas & water lines
64 | AEC Replace Windows over Wt Rm | AEC | 4 | Fall 2016 | 2 | 111 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | abate window putty and replace glass in windows over wt rm
65 | Interior Signage Project | Campus | 2 | Fall 2016 |  | 113 |  | 200000 | 0 | 200000 | 0 | 200000 | 200000 |  | Install new signs throughout campus
66 | Exterior Signage Project | Campus | 2 | Fall 2016 |  | 113 |  | 500000 | 0 | 500000 | 0 | 500000 | 500000 |  | Install new signs throughout campus
67 | Security Alarm Project | Campus | 2 | Fall 2016 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Rayco
68 | Remodel Carpenter and current Offices | M&O | 2 | Fall 2016 |  | 412 |  | 350000 | 0 | 350000 | 0 | 350000 | 350000
69 | Remodel M building | M&O | 2 | Fall 2016 | 16 | 4331 |  | 400000 | 0 | 400000 | 0 | 400000 | 400000
70 | Connect MAC to storm drain line | MAC | 4 | Fall 2016 | 2 | 419 |  | 20000 | 0 | 20000 | 0 | 20000 | 20000 |  | Trench road adjacent to MAC and connect drainage line to storm drain
71 | Install guard rail at SW corner | PAC | 2 | Fall 2016 | 2 | 113 |  | 1500 | 0 | 1500 | 0 | 1500 | 1500 |  | new rail at SW corner of PAC by lower level entrance
72 | Seed bare areas of lawns throughout campus | Grounds | 3 | Fall 2017 |  | 113 |  | 100 | 0 | 100 | 0 | 0 | 0
73 | AEC Emergency Generator Project | AEC | 2 | Hold | 6 | 113 |  | 350000 | 0 | 350000 | 0 | 350000 | 350000 |  | Design complete, seeking funding for project
74 | Widen asphalt service road between ETC and MCE | Grounds | 2 | In design |  | 113 |  | 70000 | 0 | 70000 | 0 | 0 | 0
75 | Install retaining wall and ground cover NE of WAM | Grounds | 2 | In design |  | 113 |  | 2500 | 0 | 2500 | 0 | 0 | 0
76 | Convert Cust Closet to Mech Rm | Admin | 2 | In Progress | 4 | 113 |  | 300 | 0 | 300 | 300 | 0 | 300 | No | Move custodial closet to mail room (half) and change old custodial closet to mechanical room. Replace door.
77 | AEC Office HVAC | AEC | 1 | In Progress | 5 | 113 |  | 200000 | 0 | 200000 | 200000 | 0 | 200000 | Yes | Design in progress | No project set up yet $50K
78 | Cleanup of Apprentice Yard | Campus | 4 | In Progress | 2 | 111 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Demolition of trailers, remove concrete, clean out cargo containers, get rid of pool equipment | No project set up yet
79 | Asphalt Repair work | Campus | 2 | In progress | 3 | 412 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Contract work various locations on-campus | No project set up yet
80 | Fire Alarm AA-WAM-PAC | Campus | 1 | In Progress | 8 | 419 |  | 20000 | 0 | 20000 | 0 | 20000 | 20000 | ? | Design completed, Locate conduit to connect fire alarm from AA to WAM and WAM to PAC, reprogram Math Science panel
81 | Install Sidewalk and Widen Service Road | Campus | 2 | In progress | 4 | 419 |  | 100000 | 0 | 100000 | 0 | 100000 | 100000 |  | continue new sidewalk and widen service road across from ECT
82 | Implementation of Onuma system | Campus | 2 | In progress | 52 | 113 |  | 31200 | 0 | 31200 | 0 | 31200 | 31200 | ? | integrate existing data into new Onuma system for Fac Management
83 | Facilities Master Plan project | Campus | 2 | In Progress | 52 | 113 |  | 250000 | 0 | 250000 | 250000 | 0 | 250000 | No | Upadate Facilities Master Plan. $50k spent in 2015.
84 | Relocate condenser unit on ELC | ELC | 3 | In Progress | 1 | 111 |  | 2000 | 0 | 2000 | 2000 | 0 | 2000 |  | Remove condenser from roof and install on concrete pad next to ELC | PR Approved for $20K. Will to chk if covered by bond.
85 | Paint Ext Guthrie Hall | Guthrie | 1 | In Progress |  | 412 |  | 6000 | 0 | 6000 | 6000 | 0 | 6000 | no | Prep and paint exterior of Guthrie | org 39522
86 | Guthrie Hall Connect to Emerg Gen SSC | Guthrie | 2 | In progress |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | install conduit and wiring from Guthrie to SSC
87 | LRC Install security gate at Circ Desk | LRC | 2 | In Progress |  | 113 |  | 2500 | 3208 | -708 | 2500 | 0 | 2500 | 2014 | Provide barrier between offices and reference desk 2nd floor. Approved in PR14.
88 | LRC, Tutoring Ctr & locations/ water leakage | LRC | 2 | In Progress |  | 113 |  | 10000000 | 0 | 10000000 | 0 | 10000000 | 10000000 |  | Testing and mitigation of water leakage in tutoring center and other locations within LRC
89 | MCE 125,129, 130 Replace Classrm Lighting | MCE | 2 | In Progress | 1 | 113 |  | 40000 | 0 | 40000 | 40000 | 0 | 40000 |  | lighting level too dim requires new fixtures, revise controls in 129. Approved in PR14.
90 | Replace sidewalk grates | MS | 1 | In progress | 2 | 111 |  | 2000 | 0 | 2000 | 2000 | 0 | 2000 |  | Exisiting grate not ADA compliant
91 | Install Battery Storage | North Lot | 4 | In Progress |  | 125 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Install battery storage units adjacent to North Lot and MCW
92 | Admissions & Records Security | SSC | 1 | In Progress |  | 419 |  | 10000 | 0 | 10000 | 10000 | 0 | 10000 | 2015 | create security for student records | LIB1404 processed in FY16
93 | SSC Counseling Office | SSC | 2 | In Progress |  | 419 |  | 100000 | 0 | 100000 | 100000 | 0 | 100000 | 2015 | Create private offices | PR Approved $20K
94 | Transfer Center soundproofing | SSC | 1 | In Progress | 1 | 419 |  | 50000 | 0 | 50000 | 0 | 50000 | 50000 | 2013 / 2015 | create sound proof offices | PR Approved $15K
95 | AEC Renovate Staff Locker | AEC | 3 | On hold | 8 | 419 |  | 65000 | 2020 | 62980 | 5000 | 60000 | 65000 | 2014 | Design Complete, convert staff locker room into vistor's locker room w/ access to adjacent team room. Approved in PR14. | Pr Approved 30K Proj not set up yet.
96 | AEC Repair Lower Roof/ Install Downspouts | AEC | 3 | On hold | 2 | 412 |  | 3000 | 0 | 3000 | 3000 | 0 | 3000 |  | install downspouts and splash blocks on lower roof for protection | Is this part of the West Fields inprovement project?
97 | RR Bldg at Old Aquatics area (Trailer Park) | Aquatic Ctr | 5 | On hold | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | install modular restroom bldg
98 | Financial Aid -Relocate/expand comp lab | BSC | 2 | On hold |  | 419 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | increase size of existing computer lab into adjacent spaces | Approved PR $10K
99 | Fencing - electrical equipment | Campus | 5 | On hold | 1 | 111 |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | Fence enclosures around elect. Equip, throughout campus
100 | Staff Parking Lot | Campus | 5 | On hold | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | New parking lot in south Agriculture area
101 | Install speakers in classrooms | Campus | 4 | On hold | 8 |  |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | Speakers have been purchased. Require installation in each classroom. Follow up with Grant/Jay
102 | CRC Memorial Fountain | CRC | 4 | On hold | 1 | 111 |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | Remove fountain equipment and fill with soil and plants. Reinstall plaque, water sciences water recapturing system
103 | HVAC -CSC | CSC | 5 | On hold |  | 412 |  | 100000 | 0 | 100000 | 0 | 100000 | 100000 |  | Install cooling for serving area, split system for CalWorks office, test and balance system
104 | Veteran's Ctr Renovate Restrooms | CSC | 3 | On hold | 8 | 113 |  | 18000 | 0 | 18000 | 18000 | 0 | 18000 |  | Repair and renovate restrooms and kichenette area | Org 39948
105 | Welcome Ctr & Student Ctr HVAC | CSC | 3 | On hold |  | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | Correct existing system to provide adequate HVAC
106 | Replace flooring in dining and conference rm | CSC | 1 | On hold | 2 | 113 |  | 38900 | 0 | 38900 | 0 | 38900 | 38900 |  | Replace flooring in dining area and carpet in CCCR
107 | Water Sciences at ECT | ECT | 2 | On hold | 2 | 113 |  | 5000 | 0 | 5000 | 5000 | 0 | 5000 | 2015 | Provide patio cover additional cabinets and outside watertables with demo area. Approved in PR14. | Pr Approved $25k
108 | Convert Teaching Center back to Studio | LRC | 4 | On hold |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Reestablish Studio in basement of LRC
109 | Teaching and Learning Center | LRC | 3 | On hold |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Relocate center from studio to new location in LRC | Pr Approved $80K
110 | Math Science Enclosure at North end | MS | 2 | On hold | 1 | 419 |  | 10000 | 0 | 10000 | 0 | 10000 | 10000 | 2014 | install gate and doors to restrict access to 2nd and 3rd floor areas. Under review. Problem with access. | PR Approved $150K
111 | Outside storage area | PAC | 4 | On hold |  | 113 |  | 3000 | 0 | 3000 | 3000 | 0 | 3000 |  | fence off exterior area of PAC for storage | PR Approved $100K
112 | Reseed area south of PAC | PAC | 2 | On hold | 1 | 419 |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | reseed contractor laydown area south of PAC
113 | Tennis Fence and landscape | Sportsplex | 3 | On hold |  | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | complete new fencing and landscape areas around courts
114 | Remove ivy near scoreboard | Sportsplex | 4 | On hold | 1 | 111 |  | 500 | 0 | 500 | 500 | 0 | 500 |  | Remove ivy at west side and replace with sod
115 | Enclose RRs to protect from weather | Sportsplex | 5 | On hold | 3 | 113 |  | 20000 | 0 | 20000 | 0 | 20000 | 20000 |  | Install upper wall to roof to enclose RRs, provide ventilation
116 | Seed area in front of SSC | SSC | 2 | On hold | 1 | 419 |  | 500 | 0 | 500 | 500 | 0 | 500 |  | fill in with seed areas in front of SSC
117 | Replace Exterior doors at WAM | WAM | 4 | On hold | 2 | 111 |  | 3000 | 0 | 3000 | 3000 | 0 | 3000 |  | Replace the deteriorated doors on the rear of WAM to auto shop | J Day setting up capital proj
118 | Concrete walkway to Softball Field | West Field | 3 | On hold | 3 | 113 |  | 10000 | 0 | 10000 | 0 | 10000 | 10000 |  | Walkway to provide access to Softball field bleachers
119 | Baseball seating area | West Field | 2 | On hold | 4 | 113 |  | 20000 | 0 | 20000 | 20000 | 0 | 20000 |  | repair of baseball seating area
120 | West Field Install Drinking Fountain | West Field | 5 | On hold | 1 | 111 |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | relocate and replace existing drinking fountain | PR approved $14K
121 | AEC Plaza Project | West Lot | 4 | On hold | 2 | 419 |  | 500000 | 0 | 500000 | 0 | 500000 | 500000 |  | Re-landscape planter area of circle / road / concrete area
122 | Low walls throughout Campus | Campus | 2 | Ongoing | 1 | 111 |  | 5000 | 0 | 5000 | 5000 | 0 | 5000 |  | Install skateboard guards
123 | Concrete work around campus | Campus | 2 | Ongoing | 3 | 412 |  | 20000 | 0 | 20000 | 0 | 20000 | 20000 |  | install new concrete at various locations around campus
124 | Renovate 4 offices each year | Campus | 3 | Ongoing |  | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | Renovate offices with flooring, painting, furnishing, lighting
125 | Renovate 2 restrooms each year | Campus | 3 | Ongoing |  | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | Renovate restrooms to current codes and materials
126 | Renovate 2 Classrooms each year | Campus | 3 | Ongoing | 6 | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | Renovate rooms with new flooring, blinds, lighting, and paint
127 | Math Science Restroom Renovations | MS | 2 | Ongoing | 24 | 419 |  | 45000 | 27004.53 | 17995.47 | 30000 | 15000 | 45000 | Yes | remodel all restrooms within MS
128 | Concrete driveway for baseball | Grounds | 3 | partially |  | 113 |  | 1000 | 0 | 1000 | 0 | 0 | 0
129 | Sod area south of SSC | Grounds | 4 | Redo |  | 113 |  | 300 | 0 | 300 | 0 | 0 | 0
130 | Remove ivy and replace with sod at NW corner of stadium | Grounds | 3 | Speing 2016 |  | 113 |  | 500 | 0 | 500 | 0 | 0 | 0
131 | Foster Youth Office area | CSC | 1 | Spring 2016 | 3 | 111 |  | 10000 | 0 | 10000 | 10000 | 0 | 10000 |  | Convert area within CSC for Foster Youth offices
132 | Concrete pad NE of AEC entrance | Grounds | 3 | Spring 2016 |  | 113 |  | 1000 | 0 | 1000 | 0 | 0 | 0
133 | Concrete walkway from west campus wy to softball field | Grounds | 3 | Spring 2016 |  | 113 |  | 1000 | 0 | 1000 | 0 | 0 | 0
134 | Concrete driveway from west campus wy to scoreboard area | Grounds | 3 | Spring 2016 |  | 113 |  | 2000 | 0 | 2000 | 0 | 0 | 0
135 | Access Ramp | Admin | 3 | Spring 2017 | 6 | 113 |  | 100000 | 0 | 100000 | 0 | 100000 | 100000 | NO | Handicap access to Admin Building | Scheduled Maintenance
136 | M&O Remove Car Wash Install Garage | M&O | 3 | Spring 2017 | 4 | 113 |  | 20000 | 0 | 20000 | 20000 | 0 | 20000 |  | Demo existing slab, new slab and install walls and door | org 39933
137 | Install stairs to MCW south of WAM | MCW | 4 | Spring 2017 | 3 | 419 |  | 4000 | 0 | 4000 | 0 | 4000 | 4000 |  | install stairs and railing to prevent shortcuts
138 | Lobby Offices move Switchboard | Admin | 2 | Summer 2016 | 4 | 113 |  | 30000 | 0 | 30000 | 20000 | 10000 | 30000 |  |  | org 39525
139 | Remodel AEC Lobby Restrooms | AEC | 1 | Summer 2016 | 8 | 412 |  | 285000 | 12375 | 272625 | 0 | 285000 | 285000 | Yes | remodel restrooms in lobby of large gym | org 39530
140 | Remodel C Bldg Restrooms | AEC | 1 | Summer 2016 | 8 | 412 |  | 174400 | 8625 | 165775 | 0 | 174400 | 174400 | Yes | remodel restrooms for women's/men's restroom in small gym bldg | org 39531
141 | AEC Dbl Door Replacement | AEC | 1 | Summer 2016 | 6 | 412 |  | 70000 | 0 | 70000 | 0 | 70000 | 70000 | Yes | old doors require replacement | org 39523
142 | Diesel Tech Classroom | AEP | 1 | Summer 2016 |  | 111 |  | 25000 | 0 | 25000 | 25000 | 0 | 25000 | No
143 | Financial Aid - front counter privacy | BSC | 2 | Summer 2016 |  | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2015 | install new windows and dividers for privacy.
144 | Replace fencing along Loma Vista | Campus | 1 | Summer 2016 | 2 | 412 |  | 108000 | 0 | 108000 | 0 | 108000 | 108000 |  | remove chain link fencing, install metal fence and gates along Loma Vista and Day Road
145 | Demolition of TR4, TR5 & 6 | Campus | 1 | Summer 2016 | 1 |  |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | Removal of trailer - dump fees
146 | Security System - Door Locks and PA System | Campus | 1 | Summer 2016 |  | 113 |  | 5000000 | 0 | 5000000 | 5000000 | 0 | 5000000 |  | District Initiative - $5 million from VCCCD
147 | Playground equipment at CDC | CDC | 2 | Summer 2016 | 10 | 111 |  | 5000 | 0 | 5000 | 5000 | 0 | 5000 |  | Install playground equipment, includes fall bed, relocation of sprinklers and sod
148 | Renovate CRC203 & CRC204 | CRC | 4 | Summer 2016 | 4 | 113 |  | 35000 | 0 | 35000 | 5000 | 30000 | 35000 |  | Renovate rooms with new flooring, blinds, lighting, and paint
149 | Repair Roof | CSC | 1 | Summer 2016 | 3 | 412 |  | 24000 | 0 | 24000 | 0 | 24000 | 24000 |  | Repair and reroof portion of CSC roof over Veteran's Ctr.
150 | Reroof EOPS | EOPS | 1 | Summer 2016 | 1 | 412 |  | 24000 | 0 | 24000 | 0 | 24000 | 24000 |  | repair or replace existing roof
151 | Landscape circle across from AEC | Grounds | 3 | Summer 2016 |  | 113 |  | 3000 | 0 | 3000 | 0 | 0 | 0
152 | Replace flooring in main area | Guthrie | 1 | Summer 2016 |  | 412 |  | 16500 | 0 | 16500 | 0 | 16500 | 16500 |  | replace carpet in main meeting area
153 | LRC Install curbs/waterproof 3rd Flr Mech | LRC | 4 | Summer 2016 |  | 111 |  | 5000 | 0 | 5000 | 0 | 5000 | 5000 |  | install containment curb and waterproof flooring to prevent leaks
154 | Server Room Project | LRC | 2 | Summer 2016 |  | 113 |  | 30000 | 0 | 30000 | 0 | 30000 | 30000 |  | Additional computer cooling unit for server room
155 | Oil Switch | MAC | 1 | Summer 2016 |  | 113 |  | 20000 | 0 | 20000 | 0 | 20000 | 20000 |  | Need to replace
156 | HVAC - Math Science air dryer and vacuum | MS | 1 | Summer 2016 | 3 | 412 |  | 18100 | 0 | 18100 | 0 | 18100 | 18100 |  | replace air dryer and vacuum pump
157 | Renovate SCI228 & SCI229 | MS | 1 | Summer 2016 | 2 | 412 |  | 10000 | 0 | 10000 | 2000 | 8000 | 10000 |  | Remove AV cabinet in SCI229, replace whitebds, remove door in SCI228, carpet and paint rooms, replace damaged ceiling tiles
158 | Renovate SCI230 | MS | 1 | Summer 2016 | 2 | 412 |  | 5000 | 0 | 5000 | 1000 | 4000 | 5000 |  | Remove AV cabinet, replace whitebds, new carpet and paint, replace damaged ceiling tiles
159 | Renovate SCI106 | MS | 1 | Summer 2016 | 2 | 412 |  | 5000 | 0 | 5000 | 1000 | 4000 | 5000 |  | remove fixed cabinets, paint and recarpet room
160 | Steeplechase | Sportsplex | 1 | summer 2016 |  | 419 |  | 40000 | 0 | 40000 | 0 | 40000 | 40000 | 2015 | install steeplechase pit adjacent to track | J Day setting up capital proj
161 | Refurbish Football Field | Sportsplex | 1 | Summer 2016 | 6 | 412 |  | 500000 | 0 | 500000 | 0 | 500000 | 500000 |  | Refurbish field, install new subsurface and repair/replace grass
162 | WAM Replace 2" Galv Water Line | WAM | 2 | Summer 2016 | 2 | 111 |  | 15000 | 0 | 15000 | 15000 | 0 | 15000 |  | Replace galvanized line with copper line within WAM
163 | Welding - Install Louvers | WAM | 2 | Summer 2016 | 2 | 111 |  | 5000 | 0 | 5000 | 0 | 5000 | 5000 |  | Install operable louvers in welding shop to provide proper pressure
164 | Admin Window Replacement | Admin | 1 | Summer 2016 | 4 | 412 | 412 | 140798 | 11041 | 129757 | 70000 | 70798 | 140798 | Yes | replace existing with double pane tinted windows
165 | Outside Classroom Renovation | Camarillo | 4 | Summer 2017 |  | 113 |  | 300000 | 0 | 300000 | 0 | 300000 | 300000
166 | Install Hydration Stations | Campus | 4 | Summer 2017 |  |  |  | 25000 | 0 | 25000 | 0 | 25000 | 25000 |  | Install 10 addition hydration stations
167 | Central Fire Alarm Project | Campus | 2 | Summer 2017 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
168 | Replace Hand and Guard Rails Throughout MS | MS | 2 | Summer 2017 | 16 | 412 |  | 120000 | 0 | 120000 | 0 | 120000 | 120000 |  | Replace old railings with new railings to current ADA code
169 | Repaint lines on track | Sportsplex | 3 | Summer 2017 | 3 | 113 |  | 20000 | 0 | 20000 | 0 | 0 | 0 | 2015 | repaint lines on track. Approved PR15.
170 | New Chiller Project | SSC | 1 | Summer 2017 | 2 | 113 |  | 175000 | 0 | 175000 | 0 | 0 | 0 |  | add new chiller to support only SSC and make LRC more efficient
171 | Refurbish Track | Sportsplex | 4 | Summer 2017? | 4 | 412 |  | 250000 | 0 | 250000 | 0 | 250000 | 250000 |  | resurface track and field areas
172 | Install ground cover along central campus wy | Grounds | 4 |  |  | 113 |  | 100 | 0 | 100 | 0 | 0 | 0 |  | Install ground cover along central campus wy
173 | Install ground cover at corner of south and cental campus wy | Grounds | 4 |  |  | 113 |  | 100 | 0 | 100 | 0 | 0 | 0 |  | Install ground cover at corner of south and cental campus wy
174 | Landscape area sw of tennis courts and remove tree stump | Grounds | 3 |  |  | 113 |  | 500 | 0 | 500 | 0 | 0 | 0 |  | Landscape area sw of tennis courts and remove tree stump
175 | Install ground cover adjacent to TR5 &6 | Grounds | 3 |  |  | 113 |  | 100 | 0 | 100 | 0 | 0 | 0 |  | Install ground cover adjacent to TR5 &6
176 | Install ground cover north SSC | Grounds | 3 |  |  | 113 |  | 200 | 0 | 200 | 0 | 0 | 0 |  | Install ground cover north SSC
177 | Convert fountain to planter and landscape south of CRC | Grounds | 3 |  |  | 113 |  | 200 | 0 | 200 | 0 | 0 | 0 |  | Convert fountain to planter and landscape south of CRC
179 | New stairs and railings south of stairway from WAM to MCW | Grounds | 2 |  |  | 113 |  | 8000 | 0 | 8000 | 0 | 0 | 0 |  | New stairs and railings south of stairway from WAM to MCW
180 | Resod area where TR12-TR16 were removed | Grounds | 4 |  |  | 113 |  | 15000 | 0 | 15000 | 0 | 0 | 0 |  | Resod area where TR12-TR16 were removed
181 | CDC Package Units (8) | CDC | 1 | Summer 2016 |  | Prop 39 |  | 100000 | 0 | 100000 | 0 | 0 | 0 |  | Replace 8 HVAC package units on CDC Prop 39 $100,000
182 | Warehouse Retaining Wall & Concrete | M&O | 1 | Summer 2016 |  | 113 |  | 60000 | 0 | 60000 | 0 | 0 | 0 |  | Install new retaining wall, concrete apron, and repave north end of warehouse District Funds/113 $60,000
183 | MCW/MCE North - Low Wall | MCW | 1 | Summer 2016 |  | 113 |  | 5000 | 0 | 5000 | 0 | 0 | 0 |  | Install low wall along walkway north of MCE/MCW. Fund 113 $5,000
| Totals | [6 empty] | 29036798 | 253467.53 | 28783330.47 | 5889800 | 22681398 | 28571198
changing out furniture in at least four classrooms for Gwen
We also have the paving project, move ceramics/sculpture to SAB and life drawings from CRC203 & 204 to SAB
| Relocate materials out of AEP3 | [5 empty] | 5
Fix up work at Camarillo
Work on the lock project
And Fencing project among others that I have not put out to bid yet

## Past Projects
ID # | Location | Project | Priority | Schedule | Weeks | Primary Funds | Secondary Funds | Budget | YTD | Available | M&O Work | Contract Out | Total | Program Review Approved | Description
1 | Admin | Admin Restrooms Remodel | 3 | Completed | 8 | 412 |  | 35000 | 0 | 35000 | 30000 | 5000 | 35000 |  | Contract work -Remodel men's and women's restrooms including new partitions, tile, lighting, paint, fixtures
2 | Admin | Replace HVAC in Admin | 2 | Completed | 3 | 419 |  | 25000 | 0 | 25000 | 25000 | 0 | 25000 |  | Install new boiler in custodial closet in Admin.
3 | Admin | Admin Replace stairs, install pavers | 3 | Completed | 3 | 419 |  | 50000 | 0 | 50000 | 0 | 50000 | 50000 |  | demo existing and replace with new stairs and pavers at entrance and adjacent walkways
4 | AEC | AEC Lobby Install New Drinking Fountain(s) | 4 | Completed | 3 | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | replace drinking fountain(s) to ADA standards
5 | AEC | AEC Lobby Replace Flooring | 5 | Completed | 1 | 412 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | abate floor tile and install new flooring
6 | Aquatic Ctr | Trailer Park | 5 | Denied moving forward | 26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Contract Work - pave and infrastructure for trailers, relocate trailers from campus
7 | ATP | Waterproof and drainage for ATP | 4 | Completed | 1 | 111 |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | waterproof ext. wall and install drainage system
8 | BSC | Relocate door in FYE office | 1 | Completed |  | 111 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | relocate door to create privacy for counselors in FYE
9 | BSC | Financial Aid walk-up window and work area | 2 | Completed | 1 | 113 |  | 10000 | 0 | 10000 | 0 | 10000 | 10000 | 2013 | new workstations for check-in/ computer area, new walk-up window
10 | Campus | Demolition of TR7&8 | 1 | Completed | 2 | 111 |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | Demolition of trailers, relocate power connection to TR5&6
11 | Campus | Prop 39 Yr2 LED Lighting/MS Ext Lighting | 1 | Completed | 12 | 125 | 412 | 379984 | 0 | 379984 | 0 | 379984 | 379984 |  | Replace lighting with LEDs
12 | Campus | Demolition of TR3 (Kimball Pool) | 1 | Completed | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Removal of trailer at no cost to VC
13 | Campus | Campus Lighting Project | 1 | Completed | 12 | 4331 |  | 150000 | 0 | 150000 | 0 | 150000 | 150000 |  | Replace and add new lighting throughout campus
14 | CDC | Demolition of TR9 &10 | 1 | Completed | 1 | 111 |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | Removal of trailer at no cost to VC
15 | CRC | Remodel Student Health Center | 1 | Completed | 6 | 113 |  | 60000 | 0 | 60000 | 0 | 60000 | 60000 |  | Convert restrooms to single accomodation, expand exam room
16 | CSC | Veteran's Ctr Install Security Alarm | 1 | Completed | 1 | 111 |  | 1000 | 0 | 1000 | 0 | 1000 | 1000 |  | install new security alarm
17 | CSC | Veteran's Ctr Replace Ext Door | 1 | Completed | 1 | 111 |  | 5000 | 0 | 5000 | 0 | 5000 | 5000 |  | new sliding door to replace old double doors
18 | CSC | Conference Room Door - Seal | 1 | Completed |  | 111 |  | 0 | 0 | 0 | 250 | 0 |  |  | Seal SW door
19 | CSC | ASVC Install Opening to RR in Cafeteria | 3 | Completed | 1 | 111 |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | install opening from ASVC workroom to restrooms in kitchen
20 | DRC | DRC Replace Gas Line | 1 | Completed | 2 | 111 |  | 8000 | 0 | 8000 | 4000 | 4000 | 8000 |  | New gas line connected to Campus gas, abandon existing line
21 | Grounds | Fill in trench and replace grates by AEC |  | Completed |  |  |  | 5000 | 0 | 5000 | 0 | 0 | 0
22 | Grounds | SW corner of WAM concrete sidewalk repair |  | Completed |  |  |  | 1000 | 0 | 1000 | 0 | 0 | 0
23 | Grounds | Concrete driveway from west campus wy to concession area |  | Completed |  |  |  | 1000 | 0 | 1000 | 0 | 0 | 0
24 | Grounds | Demo golf shed |  | Completed |  |  |  | 2000 | 0 | 2000 | 0 | 0 | 0
25 | Grounds | Demo TR7&8 |  | Completed |  |  |  | 500 | 0 | 500 | 0 | 0 | 0
26 | Grounds | Sod area east of BCS |  | Completed |  |  |  | 100 | 0 | 100 | 0 | 0 | 0
27 | Grounds | Sod area and install 3 palms north of LRC |  | Completed |  |  |  | 2500 | 0 | 2500 | 0 | 0 | 0
28 | Grounds | Install drain and waterproof north side of AEP |  | Completed |  |  |  | 2500 | 0 | 2500 | 0 | 0 | 0
29 | Heery Trailer | EMT Prog Create Homesetting Environ | 3 | Completed | 2 | 111 |  | 10000 | 0 | 10000 | 10000 | 0 | 10000 |  | locate and prepare space to simulate homesetting emerg ops. Approved in PR14.
30 | LRC | LRC Install Access Cover | 2 | Completed | 1 | 111 |  | 500 | 0 | 500 | 500 | 0 | 500 |  | sheet metal cover to new access for HVAC at SW corner of LRC
31 | LRC | LRC Replace Emerg Generator | 1 | Completed | 4 | 419 | 4331 | 1000 | 0 | 1000 | 1000 | 0 | 1000 |  | Install extension to conc slab, install new generator
32 | M&O | Warehouse Remove Gutter | 2 | Completed | 1 | 111 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | remove deteriorated gutter on west side of warehouse. Approved in PR14.
33 | MCW | MCW 3rd flr wall/door | 1 | Completed | 1 | 113 |  | 10000 | 0 | 10000 | 0 | 10000 | 10000 |  | new glass partition/ door to secure 3rd floor area. Approved in PR13.
34 | MS | Repair Math Sci lecture halls seating | 1 | Completed | 1 | 113 |  | 15000 | 0 | 15000 | 0 | 15000 | 15000 |  | remove fixed seating and replace with new chairs
35 | MS | Install temp HVAC for IT space | 1 | Completed |  | 111 |  | 15000 | 0 | 15000 | 15000 | 0 | 15000 |  | Install HVAC to provide cooling for IT until perm HVAC is installed
36 | MS | Repair MS116 lighting and seating | 2 | Completed | 2 | 113 | 125 | 20000 | 0 | 20000 | 0 | 20000 | 20000 |  | remove fixed seating, replace light fixtures
37 | MS | Remodel MS101 and MS105 | 1 | Completed | 4 | 113 |  | 4000 | 0 | 4000 | 4000 | 0 | 4000 |  | Demolish room within MS101 and relocate cabinets to MS105
38 | MS | Install HVAC for 1st flr offices | 2 | Completed | 24 | 113 |  | 50000 | 0 | 50000 | 0 | 50000 | 50000 |  | HVAC for 3 offices on 1st floor of Math Science
39 | MS | SCI 236 Separation Gate | 1 | Completed | 1 | 113 |  | 1500 | 0 | 1500 | 0 | 1500 | 1500 |  | gate to separate room and protect electron microscope
40 | MS | MS Replace Emerg Generator/ 3rd Flr | 1 | Completed | 4 | 4331 | 419 | 0 | 0 | 0 | 0 | 0 | 0 |  | Bond to install new generator, connect 3rd flr MS to system
41 | North Lot | Install Electric Charging Stations | 5 | Completed |  | 125 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | charging stations to be located in parking lots
42 | Sportsplex | Repair Track | 1 | Completed | 2 | 412 |  | 15000 | 0 | 15000 | 0 | 15000 | 15000 |  | contract to repair track
43 | Sportsplex | Install concrete driveway for emerg access | 1 | Completed | 2 | 113 |  | 50000 | 0 | 50000 | 0 | 50000 | 50000 |  | new driveway from Central Campus Wy to Sportsplex
44 | Sportsplex | Sportsplex RRs Install HW/Replace Faucets | 5 | Completed | 3 | 111 |  | 5000 | 0 | 5000 | 5000 | 0 | 5000 |  | Install hot water to sinks, replace faucets
45 | SSC | SSC Counseling Office | 2 | Completed | 1 | 113 |  | 500 | 0 | 500 | 500 | 0 | 500 |  | vision panels are installed in doors of counselors
46 | VCSP | Install new ADA Entry Door | 1 | Completed | 1 | 415 |  | 3000 | 0 | 3000 | 0 | 3000 | 3000 |  | Replace existing with elect sliding door ADA compliant
47 | VCSP | VCSP Acoustical Panels in Library | 1 | Completed | 1 | 113 |  | 30000 | 0 | 30000 | 0 | 30000 | 30000 |  | Install acoustical panels in library by landlord
48 | WAM | Welding - Ext Elect Connections | 2 | Completed | 1 | 113 |  | 10000 | 0 | 10000 | 0 | 10000 | 10000 |  | Awaiting Design Dwg, Contract to install exterior electrical for outdoor welding
49 | WAM | WAM Replace Gutters | 1 | Completed | 4 | 412 |  | 25000 | 0 | 25000 | 0 | 25000 | 25000 |  | Replace deteriorated gutters with new ones throughout bldg
50 | WEC | IT connectivity to Wright | 2 | Completed | 3 | 419 |  | 30000 | 0 | 30000 | 15000 | 15000 | 30000 |  | Install conduit connection between Wright Library and campus
51 | West Field | West Field fencing/ Baseball seating | 2 | Completed | 4 | 113 |  | 25000 | 0 | 25000 | 0 | 25000 | 25000 |  | fencing for west field
52 | West Field | Replace Flag & Foul Poles West Field | 2 | Completed | 2 | 113 |  | 59000 | 0 | 59000 | 9000 | 50000 | 59000 | 2014 | Install foul poles, flag pole, and repairs/ upgrades to fields
53 | West Lot | Barrier Removal Install Curb Ramps West Lot | 1 | Completed | 2 | 412 |  | 12450 | 0 | 12450 | 0 | 12450 | 12450 |  | Install curb ramps between West Lot and Central Campus Way
|  | Totals | [5 empty] | 1099534 | 0 | 1099534 | 93250 | 991934 | 1084934