VENTURA COLLEGE

Minutes of the Diversity and Culture Taskforce

Date: Wednesday 9, 2016

1:00 pm – 2:00 pm

Present: Sharon Beynon, Ben Somoza, Eileen Crump, Gwen Huddleston, Robert Lawson, Sandy Mason, Raeann Koerner, Sara Murillo, Steve Turner, Sue Royer, Nancy Mayerson, Mary Dicesare, Jocelyn Fechner, Chief Sidnam, David Carlander

Recorder:  Eileen Crump

Absent:  Ann Bittl, Trevelyn Yahr, Nathan Cole, Alex Kolesnik, Gigi Fiumerodo, Niki Milani, Lynn Wright

Minutes:

| Agenda Item | Summary of Discussion | Action (If Required) | Completion Timeline | Assigned to: |
| --- | --- | --- | --- | --- |
| Call to order | The meeting was called to order at 1:05 pm. |  |  | Gwendolyn Huddleston |
| Marketing Team | Nancy Mayerson and Mary DiCesare were present to discuss marketing strategies for the April 11 - 14, 2015 festival. The marketing team will reach out to local hotels to sponsor rooms for out-of-town visitors who will be participating in the festival. The hotel can therefore serve as an in-kind sponsor. The Marketing Team will ask Ventura City Council to designate Diversity in Culture Week for next year. The logos and website links of sponsors will be included on the printed marketing materials and online ads. There will be an information table during the festival that will include brochures and flyers from the various sponsors. The marketing team will create multimedia accounts to promote the Diversity in Culture Festival. |  |  | Eileen Crump |
| Festival Program | Sandy Mason, Sharon Beynon, Chief Sidnam and Sara Murillo will work on the event program. Sharon will work on Tag Lines for each event. The program will be sent to the marketing team for review and feedback. The Monday, April 11 Colloquium will be added to the program and designated as the kickoff event for the festival. | A meeting time will be set to develop the program. |  | Sandy Mason, Sharon Beynon, Chief Sidnam, Sara Murillo |
| Festival Events | One Book One Campus will be asking ASVC for $500 to award students prizes for Poetry Slam. OBOC will ask Rick Trevino for funds for student prizes. The Clan MacColin of Glenderry will be at the festival on Wednesday, April 13 and has requested an area with grass. There will be between 20 – 30 clan members participating in the festival. If the committee agrees to have dancers, there will be an additional $500. The clan will perform multiple shows throughout the day. Each show lasts 30 minutes. Ben Somoza is paying for the Aztec dancers with Ventura College Foundation funds. |  |  |  |
| Security for Festival | The committee agreed to set aside $1000 for 24-hour security. |  |  | Gwendolyn Huddleston |
| Sign Language Interpreters. | The college will need to hire sign language interpreters for presentations. Three speakers that will need sign interpreters are: - Phil Taggert - Astronaut - Immigration The committee agreed to set aside $1500 for the sign language interpreter. |  |  |  |
| Adjournment | The meeting was adjourned at 2:02 pm. |  |  | Gwendolyn Huddleston |