**ACCJC 2020 Midterm Report Timeline and Leads**

|  |  |  |
| --- | --- | --- |
| **Month** | **Campuses** | **District Office** |
| August/September 2019 | * Review timeline
* Discuss actions re: recommendations
 |  |
| October/November/December 2019 | * Complete gap analyses
* Form work groups for QFE review
* Complete action items to address recommendations
 | Oct 3 & Nov 1: * Work Group – 1st and 2nd meetings

Dec 13: * Campus gap analysis complete
* All gap analyses submitted to DAC
 |
| January 2020 | * Write first draft report
 | Jan 17 (?)* Work Group – 3rd meeting
 |
| February/March 2020 | * Review first draft report
* Presidents share draft report with college community for feedback
* Planning Retreats
* Review draft report
* Revise report incorporating feedback
* Final reading of revised draft
 | Feb 13: * First draft college reports submitted to DAC
 |
| April 2020 | Academic Senate* 1st and 2nd readings of revised draft

Classified Senate * Review of revised draft

Presidents * Review of revised draft
 | Apr 6: Review of revised draft reports completed through shared governance |
| May 2020 | * Finalize report incorporating feedback
* Approve final draft
 | May (?):Approve final draft at Chancellor’s CabinetMay 18: Final draft college reports due for submission to Policy, Planning and Student Success Board Committee meetingMay 21: Policy, Planning and Student Success Board Committee MeetingMay 29: Final draft college reports due for submission to June Board Agenda Review  |
| June 2020 |  | June 16: Board of Trustees meeting – 1st ReadingJune 23: Board of Trustees Strategic Planning Session – 2nd Reading/Approval |
| July/August/September 2020 | Submit final report to ACCJC |  |
| October 2020 | Oct 15: deadline for submission to ACCJC |  |